## Experiment Design V1
[7 empty] | HOUR | MINUTE | SECOND
[6 empty] | 0.75 | 2 | 45 | 0
Mission Experiment Design
Mission Phase | Start Time | Duration | Slosh Settle | End Time | MET | Mission Day | Mission Week | Maneuver | Maneuver Device | Goal | Controller
Launch & Detumble | 0:00 | 0:45 | 0:00 | 0:45 | 0:45 | 1899-12-31 00:45 | 1.1429 | Detumble | Magnatorquer X, Y, Z | Detumble and Stabilize | Standard PID | Slosh Settle Time | 0:10 | mins
Slosh Settle | 0:45 | 1:00 | 0:10 | 1:55 | 1:55 | 1899-12-31 01:55 | 1.1429 | None | None | Settle tank | Standard PID
Engineering Checkout | 1:55 | 1:30 | 0:10 | 3:35 | 3:35 | 1899-12-31 03:35 | 1.1429 | None | None | Validate Communications | Standard PID
Engineering Checkout | 3:35 | 1:30 | 0:10 | 5:15 | 5:15 | 1899-12-31 05:15 | 1.1429 | None | None | Validate Scientific Sensors | Standard PID
Engineering Checkout | 5:15 | 1:30 | 0:10 | 6:55 | 6:55 | 1899-12-31 06:55 | 1.1429 | None | None | Download sensor data | Standard PID
Baseline Validation 1 | 6:55 | 1:00 | 0:10 | 8:05 | 8:05 | 1899-12-31 08:05 | 1.1429 | Rotation (X - Longitudinal) | Reaction Wheel X | Sensor Validation; Baseline; Slosh Settle | Standard PID
Baseline Validation 2 | 8:05 | 1:00 | 0:10 | 9:15 | 9:15 | 1899-12-31 09:15 | 1.1429 | Translation (X - Longitudinal) | Thruster X | Sensor Validation; Baseline; Slosh Settle | Standard PID
Experiment Start | 9:15 | 0:00 | 0:00 | 9:15 | 9:15 | 1899-12-31 09:15 | 1.1429 | Checkout Complete --> Experiment Start
Experiment 1 | 9:15 | 1:00 | 0:10 | 10:25 | 10:25 | 1899-12-31 10:25 | 1.1429 | Translation (X - Longitudinal) | Thruster X | Control Experiment; Slosh Settle | Time Delay
Experiment 2 | 10:25 | 1:00 | 0:10 | 11:35 | 11:35 | 1899-12-31 11:35 | 1.1429 | Translation (X - Longitudinal) | Thruster X | Control Experiment; Slosh Settle | Machine Learning
Experiment 3 | 11:35 | 1:00 | 0:10 | 12:45 | 12:45 | 1899-12-31 12:45 | 1.1429 | Translation (X - Longitudinal) | Thruster X | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Experiment 4 | 12:45 | 1:00 | 0:10 | 13:55 | 13:55 | 1899-12-31 13:55 | 1.1429 | Translation (Y - Lateral) | Thruster Y | Control Experiment; Slosh Settle | Time Delay
Experiment 5 | 13:55 | 1:00 | 0:10 | 15:05 | 15:05 | 1899-12-31 15:05 | 1.1429 | Translation (Y - Lateral) | Thruster Y | Control Experiment; Slosh Settle | Machine Learning
Experiment 6 | 15:05 | 1:00 | 0:10 | 16:15 | 16:15 | 1899-12-31 16:15 | 1.1429 | Translation (Y - Lateral) | Thruster Y | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Experiment 5 | 16:15 | 1:00 | 0:10 | 17:25 | 17:25 | 1899-12-31 17:25 | 1.1429 | Rotation (X) | Reaction Wheel X | Control Experiment; Slosh Settle | Time Delay
Experiment 6 | 17:25 | 1:00 | 0:10 | 18:35 | 18:35 | 1899-12-31 18:35 | 1.1429 | Rotation (X) | Reaction Wheel X | Control Experiment; Slosh Settle | Machine Learning
Experiment 7 | 18:35 | 1:00 | 0:10 | 19:45 | 19:45 | 1899-12-31 19:45 | 1.1429 | Rotation (X) | Reaction Wheel X | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Experiment 8 | 19:45 | 1:00 | 0:10 | 20:55 | 20:55 | 1899-12-31 20:55 | 1.1429 | Rotational (Y) | Reaction Wheel Y | Control Experiment; Slosh Settle | Time Delay
Experiment 9 | 20:55 | 1:00 | 0:10 | 22:05 | 22:05 | 1899-12-31 22:05 | 1.1429 | Rotational (Y) | Reaction Wheel Y | Control Experiment; Slosh Settle | Machine Learning
Experiment 10 | 22:05 | 1:00 | 0:10 | 23:15 | 23:15 | 1899-12-31 23:15 | 1.1429 | Rotational (Y) | Reaction Wheel Y | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Baseline Validation 2 | 23:15 | 1:00 | 0:10 | 24:25 | 24:25 | 1900-01-01 00:25 | 1.2857 | Rotational (X,Y) | Reaction Wheel X, Y | Baseline; Slosh Settle | Standard PID
Experiment 11 | 24:25 | 1:00 | 0:10 | 25:35 | 25:35 | 1900-01-01 01:35 | 1.2857 | Rotational (X,Y) | Reaction Wheel X, Y | Control Experiment; Slosh Settle | Time Delay
Experiment 12 | 25:35 | 1:00 | 0:10 | 26:45 | 26:45 | 1900-01-01 02:45 | 1.2857 | Rotational (X,Y) | Reaction Wheel X, Y | Control Experiment; Slosh Settle | Machine Learning
Experiment 13 | 26:45 | 1:00 | 0:10 | 27:55 | 27:55 | 1900-01-01 03:55 | 1.2857 | Rotational (X,Y) | Reaction Wheel X, Y | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Baseline Validation 3 | 27:55 | 1:00 | 0:10 | 29:05 | 29:05 | 1900-01-01 05:05 | 1.2857 | Rotational (X) + Translation (X) | Reaction Wheel X, Thruster X | Baseline; Slosh Settle | Standard PID
Experiment 14 | 29:05 | 1:00 | 0:10 | 30:15 | 30:15 | 1900-01-01 06:15 | 1.2857 | Rotational (X) + Translation (X) | Reaction Wheel X, Thruster X | Control Experiment; Slosh Settle | Time Delay
Experiment 15 | 30:15 | 1:00 | 0:10 | 31:25 | 31:25 | 1900-01-01 07:25 | 1.2857 | Rotational (X) + Translation (X) | Reaction Wheel X, Thruster X | Control Experiment; Slosh Settle | Machine Learning
Experiment 16 | 31:25 | 1:00 | 0:10 | 32:35 | 32:35 | 1900-01-01 08:35 | 1.2857 | Rotational (X) + Translation (X) | Reaction Wheel X, Thruster X | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Baseline Validation 4 | 32:35 | 1:00 | 0:10 | 33:45 | 33:45 | 1900-01-01 09:45 | 1.2857 | Rotational (X,Y) + Translation (X) | Reaction Wheel X,Y, Thruster X | Baseline; Slosh Settle | Standard PID
Experiment 17 | 33:45 | 1:00 | 0:10 | 34:55 | 34:55 | 1900-01-01 10:55 | 1.2857 | Rotational (X,Y) + Translation (X) | Reaction Wheel X,Y, Thruster X | Control Experiment; Slosh Settle | Time Delay
Experiment 18 | 34:55 | 1:00 | 0:10 | 36:05 | 36:05 | 1900-01-01 12:05 | 1.2857 | Rotational (X,Y) + Translation (X) | Reaction Wheel X,Y, Thruster X | Control Experiment; Slosh Settle | Machine Learning
Experiment 19 | 36:05 | 1:00 | 0:10 | 37:15 | 37:15 | 1900-01-01 13:15 | 1.2857 | Rotational (X,Y) + Translation (X) | Reaction Wheel X,Y, Thruster X | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Baseline Validation 5 | 37:15 | 1:00 | 0:10 | 38:25 | 38:25 | 1900-01-01 14:25 | 1.2857 | Rotational (X,Y) + Translation (Y) | Reaction Wheel X,Y, Thruster Y | Baseline; Slosh Settle | Standard PID
Experiment 20 | 38:25 | 1:00 | 0:10 | 39:35 | 39:35 | 1900-01-01 15:35 | 1.2857 | Rotational (X,Y) + Translation (Y) | Reaction Wheel X,Y, Thruster Y | Control Experiment; Slosh Settle | Time Delay
Experiment 21 | 39:35 | 1:00 | 0:10 | 40:45 | 40:45 | 1900-01-01 16:45 | 1.2857 | Rotational (X,Y) + Translation (Y) | Reaction Wheel X,Y, Thruster Y | Control Experiment; Slosh Settle | Machine Learning
Experiment 22 | 40:45 | 1:00 | 0:10 | 41:55 | 41:55 | 1900-01-01 17:55 | 1.2857 | Rotational (X,Y) + Translation (Y) | Reaction Wheel X,Y, Thruster Y | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Thrusters Expended
Baseline Validation 6 | 41:55 | 1:00 | 0:10 | 43:05 | 43:05 | 1900-01-01 19:05 | 1.2857 | Nutational (Z,Y,Z) | Reaction Wheel X,Y, Z | Baseline; Slosh Settle | Standard PID
Experiment 20 | 43:05 | 1:00 | 0:10 | 44:15 | 44:15 | 1900-01-01 20:15 | 1.2857 | Nutational (Z,Y,Z) | Reaction Wheel X,Y, Z | Control Experiment; Slosh Settle | Time Delay
Experiment 21 | 44:15 | 1:00 | 0:10 | 45:25 | 45:25 | 1900-01-01 21:25 | 1.2857 | Nutational (Z,Y,Z) | Reaction Wheel X,Y, Z | Control Experiment; Slosh Settle | Machine Learning
Experiment 22 | 45:25 | 1:00 | 0:10 | 46:35 | 46:35 | 1900-01-01 22:35 | 1.2857 | Nutational (Z,Y,Z) | Reaction Wheel X,Y, Z | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Baseline Validation 7 | 46:35 | 1:00 | 0:10 | 47:45 | 47:45 | 1900-01-01 23:45 | 1.2857 | TBD | TBD | Baseline; Slosh Settle | Standard PID
Experiment 23 | 47:45 | 1:00 | 0:10 | 48:55 | 48:55 | 1900-01-02 00:55 | 1.4286 | TBD | TBD | Control Experiment; Slosh Settle | Time Delay
Experiment 24 | 48:55 | 1:00 | 0:10 | 50:05 | 50:05 | 1900-01-02 02:05 | 1.4286 | TBD | TBD | Control Experiment; Slosh Settle | Machine Learning
Experiment 25 | 50:05 | 1:00 | 0:10 | 51:15 | 51:15 | 1900-01-02 03:15 | 1.4286 | TBD | TBD | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Baseline Validation 8 | 51:15 | 1:00 | 0:10 | 52:25 | 52:25 | 1900-01-02 04:25 | 1.4286 | TBD | TBD | Baseline; Slosh Settle | Standard PID
Experiment 26 | 52:25 | 1:00 | 0:10 | 53:35 | 53:35 | 1900-01-02 05:35 | 1.4286 | TBD | TBD | Control Experiment; Slosh Settle | Time Delay
Experiment 27 | 53:35 | 1:00 | 0:10 | 54:45 | 54:45 | 1900-01-02 06:45 | 1.4286 | TBD | TBD | Control Experiment; Slosh Settle | Machine Learning
Experiment 28 | 54:45 | 180:00 | 0:10 | 234:55 | 234:55 | 1900-01-09 18:55 | 2 | TBD | TBD | Control Experiment; Slosh Settle | TD + ML + Ref Governor
Time Format: HH:MM |  |  |  |  | Time Format: HH:MM:SS
Formulas:
Mission Day = [MET]+1
Increasing Maneuver Complexity
Rotational Only

## Experiment Design V2
Mission Experiment Design
Experiment # | Phase | Experiment Name | Angle | Velocity | Mission Day | Maneuver | Rotation Axis | Camera | Mission Phase | Goal | Controller
1 | A | A1 | 10 | 8 | 1 | 1-axis | X | On | Minimum Success | Initial training data | BCT
2 | A | A2 | 40 | 8 | 2 | 1-axis | X | On | Minimum Success | Initial training data | BCT
3 | A | A3 | 60 | 8 | 3 | 1-axis | X | On | Minimum Success | Initial training data | BCT
4 | A | A4 | 90 | 8 | 4 | 1-axis | X | On | Minimum Success | Initial training data | BCT
5 | A | A5 | 120 | 8 | 5 | 1-axis | X | On | Minimum Success | Initial training data | BCT
6 | A | A6 | 160 | 8 | 6 | 1-axis | X | On | Minimum Success | Initial training data | BCT
7 | A | A7 | 180 | 8 | 7 | 1-axis | X | On | Minimum Success | Initial training data | BCT
8 | A | A8 | 360 | 8 | 8 | 1-axis | X | On | Minimum Success | Initial training data | BCT
9 | A | A9 | 10 | 10 | 9 | 1-axis | X | On | Minimum Success | Initial training data | BCT
10 | A | A10 | 40 | 10 | 10 | 1-axis | X | On | Minimum Success | Initial training data | BCT
11 | A | A11 | 60 | 10 | 11 | 1-axis | X | On | Minimum Success | Initial training data | BCT
12 | A | A12 | 90 | 10 | 12 | 1-axis | X | On | Minimum Success | Initial training data | BCT
13 | A | A13 | 120 | 10 | 13 | 1-axis | X | On | Minimum Success | Initial training data | BCT
14 | A | A14 | 160 | 10 | 14 | 1-axis | X | On | Minimum Success | Initial training data | BCT
15 | A | A15 | 180 | 10 | 15 | 1-axis | X | On | Minimum Success | Initial training data | BCT
16 | A | A16 | 360 | 10 | 16 | 1-axis | X | On | Minimum Success | Initial training data | BCT
17 | A | A17 | 10 | 15 | 17 | 1-axis | X | On | Minimum Success | Initial training data | BCT
18 | A | A18 | 40 | 15 | 18 | 1-axis | X | On | Minimum Success | Initial training data | BCT
19 | A | A19 | 60 | 15 | 19 | 1-axis | X | On | Minimum Success | Initial training data | BCT
20 | A | A20 | 90 | 15 | 20 | 1-axis | X | On | Minimum Success | Initial training data | BCT
21 | A | A21 | 120 | 15 | 21 | 1-axis | X | On | Minimum Success | Initial training data | BCT
22 | A | A22 | 160 | 15 | 22 | 1-axis | X | On | Minimum Success | Initial training data | BCT
23 | A | A23 | 180 | 15 | 23 | 1-axis | X | On | Minimum Success | Initial training data | BCT
24 | A | A24 | 360 | 15 | 24 | 1-axis | X | On | Minimum Success | Initial training data | BCT
25 | A | A25 | 10 | 18 | 25 | 1-axis | X | On | Minimum Success | Initial training data | BCT
26 | A | A26 | 40 | 18 | 26 | 1-axis | X | On | Minimum Success | Initial training data | BCT
27 | A | A27 | 60 | 18 | 27 | 1-axis | X | On | Minimum Success | Initial training data | BCT
28 | A | A28 | 90 | 18 | 28 | 1-axis | X | On | Minimum Success | Initial training data | BCT
29 | A | A29 | 120 | 18 | 29 | 1-axis | X | On | Minimum Success | Initial training data | BCT
30 | A | A30 | 160 | 18 | 30 | 1-axis | X | On | Minimum Success | Initial training data | BCT
31 | A | A31 | 180 | 18 | 31 | 1-axis | X | On | Minimum Success | Initial training data | BCT
32 | A | A32 | 360 | 18 | 32 | 1-axis | X | On | Minimum Success | Initial training data | BCT
33 | A | A33 | 10 | 20 | 33 | 1-axis | X | On | Minimum Success | Initial training data | BCT
34 | A | A34 | 40 | 20 | 34 | 1-axis | X | On | Minimum Success | Initial training data | BCT
35 | A | A35 | 60 | 20 | 35 | 1-axis | X | On | Minimum Success | Initial training data | BCT
36 | A | A36 | 90 | 20 | 36 | 1-axis | X | On | Minimum Success | Initial training data | BCT
37 | A | A37 | 120 | 20 | 37 | 1-axis | X | On | Minimum Success | Initial training data | BCT
38 | A | A38 | 160 | 20 | 38 | 1-axis | X | On | Minimum Success | Initial training data | BCT
39 | A | A39 | 180 | 20 | 39 | 1-axis | X | On | Minimum Success | Initial training data | BCT
40 | A | A40 | 360 | 20 | 40 | 1-axis | X | On | Minimum Success | Initial training data | BCT
UPLOAD CONTROLLER
41 | A | A41 | 360 | 20 | 41 | 1-axis | X | On | Full Mission | Excite --> Observe | BCT
42 | A | A42 | 360 | 20 | 42 | 1-axis | X | Off | Full Mission | Excite --> Observe | BCT
43 | A | A43 | 360 | 20 | 43 | 1-axis | X | Off | Full Mission | Excite --> Observe | BCT
44 | A | A44 | 360 | 20 | 44 | 1-axis | Y | On | Full Mission | Excite --> Observe | BCT
45 | A | A45 | 360 | 20 | 45 | 1-axis | Y | Off | Full Mission | Excite --> Observe | BCT
46 | A | A46 | 360 | 20 | 46 | 1-axis | Y | Off | Full Mission | Excite --> Observe | BCT
47 | A | A47 | 360 | 20 | 47 | 1-axis | Z | On | Full Mission | Excite --> Observe | BCT
48 | A | A48 | 360 | 20 | 48 | 1-axis | Z | Off | Full Mission | Excite --> Observe | BCT
49 | A | A49 | 360 | 20 | 49 | 1-axis | Z | Off | Full Mission | Excite --> Observe | BCT
50 | A | A50 | 360 | 20 | 50 | 2-axis | XY | On | Full Mission | Excite --> Observe | BCT
51 | A | A51 | 360 | 20 | 51 | 2-axis | XY | Off | Full Mission | Excite --> Observe | BCT
52 | A | A52 | 360 | 20 | 52 | 2-axis | XY | Off | Full Mission | Excite --> Observe | BCT
53 | A | A53 | 360 | 20 | 53 | 2-axis | XZ | On | Full Mission | Excite --> Observe | BCT
54 | A | A54 | 360 | 20 | 54 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | BCT
55 | A | A55 | 360 | 20 | 55 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | BCT
56 | A | A56 | 360 | 20 | 56 | 2-axis | YZ | On | Full Mission | Excite --> Observe | BCT
57 | A | A57 | 360 | 20 | 57 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | BCT
58 | A | A58 | 360 | 20 | 58 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | BCT
59 | A | A59 | 360 | 20 | 59 | 3-axis | XYZ | On | Full Mission | Excite --> Observe | BCT
60 | A | A60 | 360 | 20 | 60 | 3-axis | XYZ | Off | Full Mission | Excite --> Observe | BCT
61 | A | A61 | 360 | 20 | 61 | 3-axis | XYZ | Off | Full Mission | Excite --> Observe | BCT
UPLOAD CONTROLLER
62 | B | B1 | 360 | 20 | 62 | 1-axis | X | On | Full Mission | Excite --> Observe | Output Feedback
63 | B | B2 | 360 | 20 | 63 | 1-axis | X | Off | Full Mission | Excite --> Observe | Output Feedback
64 | B | B3 | 360 | 20 | 64 | 1-axis | X | Off | Full Mission | Excite --> Observe | Output Feedback
65 | B | B4 | 360 | 20 | 65 | 1-axis | Y | On | Full Mission | Excite --> Observe | Output Feedback
66 | B | B5 | 360 | 20 | 66 | 1-axis | Y | Off | Full Mission | Excite --> Observe | Output Feedback
67 | B | B6 | 360 | 20 | 67 | 1-axis | Y | Off | Full Mission | Excite --> Observe | Output Feedback
68 | B | B7 | 360 | 20 | 68 | 1-axis | Z | On | Full Mission | Excite --> Observe | Output Feedback
69 | B | B8 | 360 | 20 | 69 | 1-axis | Z | Off | Full Mission | Excite --> Observe | Output Feedback
70 | B | B9 | 360 | 20 | 70 | 1-axis | Z | Off | Full Mission | Excite --> Observe | Output Feedback
71 | B | B10 | 360 | 20 | 71 | 1-axis | X | On | Full Mission | Excite --> Mitigate | Output Feedback
72 | B | B11 | 360 | 20 | 72 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | Output Feedback
73 | B | B12 | 360 | 20 | 73 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | Output Feedback
74 | B | B13 | 360 | 20 | 74 | 1-axis | Y | On | Full Mission | Excite --> Mitigate | Output Feedback
75 | B | B14 | 360 | 20 | 75 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | Output Feedback
76 | B | B15 | 360 | 20 | 76 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | Output Feedback
77 | B | B16 | 360 | 20 | 77 | 1-axis | Z | On | Full Mission | Excite --> Mitigate | Output Feedback
78 | B | B17 | 360 | 20 | 78 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | Output Feedback
79 | B | B18 | 360 | 20 | 79 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | Output Feedback
80 | B | B19 | 360 | 20 | 80 | 2-axis | XY | On | Full Mission | Excite --> Observe | Output Feedback
81 | B | B20 | 360 | 20 | 81 | 2-axis | XY | Off | Full Mission | Excite --> Observe | Output Feedback
82 | B | B21 | 360 | 20 | 82 | 2-axis | XY | Off | Full Mission | Excite --> Observe | Output Feedback
83 | B | B22 | 360 | 20 | 83 | 2-axis | XZ | On | Full Mission | Excite --> Observe | Output Feedback
84 | B | B23 | 360 | 20 | 84 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | Output Feedback
85 | B | B24 | 360 | 20 | 85 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | Output Feedback
86 | B | B25 | 360 | 20 | 86 | 2-axis | YZ | On | Full Mission | Excite --> Observe | Output Feedback
87 | B | B26 | 360 | 20 | 87 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | Output Feedback
88 | B | B27 | 360 | 20 | 88 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | Output Feedback
89 | B | B28 | 360 | 20 | 89 | 2-axis | XY | On | Full Mission | Excite --> Mitigate | Output Feedback
90 | B | B29 | 360 | 20 | 90 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | Output Feedback
91 | B | B30 | 360 | 20 | 91 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | Output Feedback
92 | B | B31 | 360 | 20 | 92 | 2-axis | XZ | On | Full Mission | Excite --> Mitigate | Output Feedback
93 | B | B32 | 360 | 20 | 93 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | Output Feedback
94 | B | B33 | 360 | 20 | 94 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | Output Feedback
95 | B | B34 | 360 | 20 | 95 | 2-axis | YZ | On | Full Mission | Excite --> Mitigate | Output Feedback
96 | B | B35 | 360 | 20 | 96 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | Output Feedback
97 | B | B36 | 360 | 20 | 97 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | Output Feedback
98 | B | B37 | 360 | 20 | 98 | 3-axis | ZYX | On | Full Mission | Excite --> Observe | Output Feedback
99 | B | B38 | 360 | 20 | 99 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | Output Feedback
100 | B | B39 | 360 | 20 | 100 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | Output Feedback
101 | B | B40 | 360 | 20 | 101 | 3-axis | ZYX | On | Full Mission | Excite --> Mitigate | Output Feedback
102 | B | B41 | 360 | 20 | 102 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | Output Feedback
103 | B | B42 | 360 | 20 | 103 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | Output Feedback
UPLOAD CONTROLLER
104 | C | C1 | 360 | 20 | 104 | 1-axis | X | On | Full Mission | Excite --> Observe | ML Controller
105 | C | C2 | 360 | 20 | 105 | 1-axis | X | Off | Full Mission | Excite --> Observe | ML Controller
106 | C | C3 | 360 | 20 | 106 | 1-axis | X | Off | Full Mission | Excite --> Observe | ML Controller
107 | C | C4 | 360 | 20 | 107 | 1-axis | Y | On | Full Mission | Excite --> Observe | ML Controller
108 | C | C5 | 360 | 20 | 108 | 1-axis | Y | Off | Full Mission | Excite --> Observe | ML Controller
109 | C | C6 | 360 | 20 | 109 | 1-axis | Y | Off | Full Mission | Excite --> Observe | ML Controller
110 | C | C7 | 360 | 20 | 110 | 1-axis | Z | On | Full Mission | Excite --> Observe | ML Controller
111 | C | C8 | 360 | 20 | 111 | 1-axis | Z | Off | Full Mission | Excite --> Observe | ML Controller
112 | C | C9 | 360 | 20 | 112 | 1-axis | Z | Off | Full Mission | Excite --> Observe | ML Controller
113 | C | C10 | 360 | 20 | 113 | 1-axis | X | On | Full Mission | Excite --> Mitigate | ML Controller
114 | C | C11 | 360 | 20 | 114 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | ML Controller
115 | C | C12 | 360 | 20 | 115 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | ML Controller
116 | C | C13 | 360 | 20 | 116 | 1-axis | Y | On | Full Mission | Excite --> Mitigate | ML Controller
117 | C | C14 | 360 | 20 | 117 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | ML Controller
118 | C | C15 | 360 | 20 | 118 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | ML Controller
119 | C | C16 | 360 | 20 | 119 | 1-axis | Z | On | Full Mission | Excite --> Mitigate | ML Controller
120 | C | C17 | 360 | 20 | 120 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | ML Controller
121 | C | C18 | 360 | 20 | 121 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | ML Controller
122 | C | C19 | 360 | 20 | 122 | 2-axis | XY | On | Full Mission | Excite --> Observe | ML Controller
123 | C | C20 | 360 | 20 | 123 | 2-axis | XY | Off | Full Mission | Excite --> Observe | ML Controller
124 | C | C21 | 360 | 20 | 124 | 2-axis | XY | Off | Full Mission | Excite --> Observe | ML Controller
125 | C | C22 | 360 | 20 | 125 | 2-axis | XZ | On | Full Mission | Excite --> Observe | ML Controller
126 | C | C23 | 360 | 20 | 126 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | ML Controller
127 | C | C24 | 360 | 20 | 127 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | ML Controller
128 | C | C25 | 360 | 20 | 128 | 2-axis | YZ | On | Full Mission | Excite --> Observe | ML Controller
129 | C | C26 | 360 | 20 | 129 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | ML Controller
130 | C | C27 | 360 | 20 | 130 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | ML Controller
131 | C | C28 | 360 | 20 | 131 | 2-axis | XY | On | Full Mission | Excite --> Mitigate | ML Controller
132 | C | C29 | 360 | 20 | 132 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | ML Controller
133 | C | C30 | 360 | 20 | 133 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | ML Controller
134 | C | C31 | 360 | 20 | 134 | 2-axis | XZ | On | Full Mission | Excite --> Mitigate | ML Controller
135 | C | C32 | 360 | 20 | 135 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | ML Controller
136 | C | C33 | 360 | 20 | 136 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | ML Controller
137 | C | C34 | 360 | 20 | 137 | 2-axis | YZ | On | Full Mission | Excite --> Mitigate | ML Controller
138 | C | C35 | 360 | 20 | 138 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | ML Controller
139 | C | C36 | 360 | 20 | 139 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | ML Controller
140 | C | C37 | 360 | 20 | 140 | 3-axis | ZYX | On | Full Mission | Excite --> Observe | ML Controller
141 | C | C38 | 360 | 20 | 141 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | ML Controller
142 | C | C39 | 360 | 20 | 142 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | ML Controller
143 | C | C40 | 360 | 20 | 143 | 3-axis | ZYX | On | Full Mission | Excite --> Mitigate | ML Controller
144 | C | C41 | 360 | 20 | 144 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | ML Controller
145 | C | C42 | 360 | 20 | 145 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | ML Controller
UPLOAD CONTROLLER
146 | D | D1 | 360 | 20 | 146 | 1-axis | X | On | Full Mission | Excite --> Observe | Reference Governor
147 | D | D2 | 360 | 20 | 147 | 1-axis | X | Off | Full Mission | Excite --> Observe | Reference Governor
148 | D | D3 | 360 | 20 | 148 | 1-axis | X | Off | Full Mission | Excite --> Observe | Reference Governor
149 | D | D4 | 360 | 20 | 149 | 1-axis | Y | On | Full Mission | Excite --> Observe | Reference Governor
150 | D | D5 | 360 | 20 | 150 | 1-axis | Y | Off | Full Mission | Excite --> Observe | Reference Governor
151 | D | D6 | 360 | 20 | 151 | 1-axis | Y | Off | Full Mission | Excite --> Observe | Reference Governor
152 | D | D7 | 360 | 20 | 152 | 1-axis | Z | On | Full Mission | Excite --> Observe | Reference Governor
153 | D | D8 | 360 | 20 | 153 | 1-axis | Z | Off | Full Mission | Excite --> Observe | Reference Governor
154 | D | D9 | 360 | 20 | 154 | 1-axis | Z | Off | Full Mission | Excite --> Observe | Reference Governor
155 | D | D10 | 360 | 20 | 155 | 1-axis | X | On | Full Mission | Excite --> Mitigate | Reference Governor
156 | D | D11 | 360 | 20 | 156 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | Reference Governor
157 | D | D12 | 360 | 20 | 157 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | Reference Governor
158 | D | D13 | 360 | 20 | 158 | 1-axis | Y | On | Full Mission | Excite --> Mitigate | Reference Governor
159 | D | D14 | 360 | 20 | 159 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | Reference Governor
160 | D | D15 | 360 | 20 | 160 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | Reference Governor
161 | D | D16 | 360 | 20 | 161 | 1-axis | Z | On | Full Mission | Excite --> Mitigate | Reference Governor
162 | D | D17 | 360 | 20 | 162 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | Reference Governor
163 | D | D18 | 360 | 20 | 163 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | Reference Governor
164 | D | D19 | 360 | 20 | 164 | 2-axis | XY | On | Full Mission | Excite --> Observe | Reference Governor
165 | D | D20 | 360 | 20 | 165 | 2-axis | XY | Off | Full Mission | Excite --> Observe | Reference Governor
166 | D | D21 | 360 | 20 | 166 | 2-axis | XY | Off | Full Mission | Excite --> Observe | Reference Governor
167 | D | D22 | 360 | 20 | 167 | 2-axis | XZ | On | Full Mission | Excite --> Observe | Reference Governor
168 | D | D23 | 360 | 20 | 168 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | Reference Governor
169 | D | D24 | 360 | 20 | 169 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | Reference Governor
170 | D | D25 | 360 | 20 | 170 | 2-axis | YZ | On | Full Mission | Excite --> Observe | Reference Governor
171 | D | D26 | 360 | 20 | 171 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | Reference Governor
172 | D | D27 | 360 | 20 | 172 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | Reference Governor
173 | D | D28 | 360 | 20 | 173 | 2-axis | XY | On | Full Mission | Excite --> Mitigate | Reference Governor
174 | D | D29 | 360 | 20 | 174 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | Reference Governor
175 | D | D30 | 360 | 20 | 175 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | Reference Governor
176 | D | D31 | 360 | 20 | 176 | 2-axis | XZ | On | Full Mission | Excite --> Mitigate | Reference Governor
177 | D | D32 | 360 | 20 | 177 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | Reference Governor
178 | D | D33 | 360 | 20 | 178 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | Reference Governor
179 | D | D34 | 360 | 20 | 179 | 2-axis | YZ | On | Full Mission | Excite --> Mitigate | Reference Governor
180 | D | D35 | 360 | 20 | 180 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | Reference Governor
181 | D | D36 | 360 | 20 | 181 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | Reference Governor
182 | D | D37 | 360 | 20 | 182 | 3-axis | ZYX | On | Full Mission | Excite --> Observe | Reference Governor
183 | D | D38 | 360 | 20 | 183 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | Reference Governor | Entry Constraints
184 | D | D39 | 360 | 20 | 184 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | Reference Governor | Success Criteria
185 | D | D40 | 360 | 20 | 185 | 3-axis | ZYX | On | Full Mission | Excite --> Mitigate | Reference Governor | Data Products
186 | D | D41 | 360 | 20 | 186 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | Reference Governor | Ground Config
187 | D | D42 | 360 | 20 | 187 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | Reference Governor | Spacecraft Config
UPLOAD CONTROLLER
188 | E | E1 | 360 | 20 | 188 | 1-axis | X | On | Full Mission | Excite --> Observe | Output+ML+RG
189 | E | E2 | 360 | 20 | 189 | 1-axis | X | Off | Full Mission | Excite --> Observe | Output+ML+RG
190 | E | E3 | 360 | 20 | 190 | 1-axis | X | Off | Full Mission | Excite --> Observe | Output+ML+RG
191 | E | E4 | 360 | 20 | 191 | 1-axis | Y | On | Full Mission | Excite --> Observe | Output+ML+RG
192 | E | E5 | 360 | 20 | 192 | 1-axis | Y | Off | Full Mission | Excite --> Observe | Output+ML+RG
193 | E | E6 | 360 | 20 | 193 | 1-axis | Y | Off | Full Mission | Excite --> Observe | Output+ML+RG
194 | E | E7 | 360 | 20 | 194 | 1-axis | Z | On | Full Mission | Excite --> Observe | Output+ML+RG
195 | E | E8 | 360 | 20 | 195 | 1-axis | Z | Off | Full Mission | Excite --> Observe | Output+ML+RG
196 | E | E9 | 360 | 20 | 196 | 1-axis | Z | Off | Full Mission | Excite --> Observe | Output+ML+RG
197 | E | E10 | 360 | 20 | 197 | 1-axis | X | On | Full Mission | Excite --> Mitigate | Output+ML+RG
198 | E | E11 | 360 | 20 | 198 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
199 | E | E12 | 360 | 20 | 199 | 1-axis | X | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
200 | E | E13 | 360 | 20 | 200 | 1-axis | Y | On | Full Mission | Excite --> Mitigate | Output+ML+RG
201 | E | E14 | 360 | 20 | 201 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
202 | E | E15 | 360 | 20 | 202 | 1-axis | Y | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
203 | E | E16 | 360 | 20 | 203 | 1-axis | Z | On | Full Mission | Excite --> Mitigate | Output+ML+RG
204 | E | E17 | 360 | 20 | 204 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
205 | E | E18 | 360 | 20 | 205 | 1-axis | Z | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
206 | E | E19 | 360 | 20 | 206 | 2-axis | XY | On | Full Mission | Excite --> Observe | Output+ML+RG
207 | E | E20 | 360 | 20 | 207 | 2-axis | XY | Off | Full Mission | Excite --> Observe | Output+ML+RG
208 | E | E21 | 360 | 20 | 208 | 2-axis | XY | Off | Full Mission | Excite --> Observe | Output+ML+RG
209 | E | E22 | 360 | 20 | 209 | 2-axis | XZ | On | Full Mission | Excite --> Observe | Output+ML+RG
210 | E | E23 | 360 | 20 | 210 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | Output+ML+RG
211 | E | E24 | 360 | 20 | 211 | 2-axis | XZ | Off | Full Mission | Excite --> Observe | Output+ML+RG
212 | E | E25 | 360 | 20 | 212 | 2-axis | YZ | On | Full Mission | Excite --> Observe | Output+ML+RG
213 | E | E26 | 360 | 20 | 213 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | Output+ML+RG
214 | E | E27 | 360 | 20 | 214 | 2-axis | YZ | Off | Full Mission | Excite --> Observe | Output+ML+RG
215 | E | E28 | 360 | 20 | 215 | 2-axis | XY | On | Full Mission | Excite --> Mitigate | Output+ML+RG
216 | E | E29 | 360 | 20 | 216 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
217 | E | E30 | 360 | 20 | 217 | 2-axis | XY | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
218 | E | E31 | 360 | 20 | 218 | 2-axis | XZ | On | Full Mission | Excite --> Mitigate | Output+ML+RG
219 | E | E32 | 360 | 20 | 219 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
220 | E | E33 | 360 | 20 | 220 | 2-axis | XZ | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
221 | E | E34 | 360 | 20 | 221 | 2-axis | YZ | On | Full Mission | Excite --> Mitigate | Output+ML+RG
222 | E | E35 | 360 | 20 | 222 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
223 | E | E36 | 360 | 20 | 223 | 2-axis | YZ | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
224 | E | E37 | 360 | 20 | 224 | 3-axis | ZYX | On | Full Mission | Excite --> Observe | Output+ML+RG
225 | E | E38 | 360 | 20 | 225 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | Output+ML+RG
226 | E | E39 | 360 | 20 | 226 | 3-axis | ZYX | Off | Full Mission | Excite --> Observe | Output+ML+RG
227 | E | E40 | 360 | 20 | 227 | 3-axis | ZYX | On | Full Mission | Excite --> Mitigate | Output+ML+RG
228 | E | E41 | 360 | 20 | 228 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
229 | E | E42 | 360 | 20 | 229 | 3-axis | ZYX | Off | Full Mission | Excite --> Mitigate | Output+ML+RG
DONE
[7 empty] | Camera On | 103 | 44.98%
[7 empty] | Camera Off | 126 | 55.02%
[7 empty] | TOTAL | 229
Minimum Mission Criteria
Multi-Axis Observation
Output Feedback
Machine Learning
Reference Governor
Output Feedback + ML + RG